## Migration Accounts
Our O365 Migration Experience - Major customers
Customer | Source | Target | Content DB Size | Tools Used | Duration Taken | Effort Required | Challenges Faced | Any Reusable Asset | Comments
One of the top American providers of industrial automation and information products | SP 2010 & 2013 | SP Online & On-Prem | 1.5 TB + | Metalogix Content Matrix and Dell Migration Suite | 6 Months | 2 Onsite and 6 Offshore | 1. Moving the following - List InfoPath forms + SharePoint Designer Workflows + DVWP and DFWP 2. JavaScript Pop-ups not supported and must be moved to Callouts in O365 3. Share Feature - This creates lots of confusion and issues during UAT phases. Enabling this feature. 4. Office 365 do not support InfoPath forms web services specifically (Forms for web browser support only) the one which gets the current user name. 5. Security Management - Managing security in O365 could be quite tricky comparing to 2010 environment. | ControlPoint was quite helpful and did an excellent (PowerShell is other option) | Migration tool support (Must be Premium Support, available for 24*7*365). Sometime is critical and may need a deep discussion with Metalogix or dell associate.
Finnish multinational communications and IT company | SP 2010 Online | SP2013 Online | 3 TB+ | Metalogix | 9 Months | 12 resources | Issues related to Cloud App Model , Responsive Design implementation issues | Reusable services as a workaround for CAM challenges | Successful conversion to CSOM (including OOTB mapping & simplification), Well planned Site collection segregation with full migration
An Australian engineering company | SP 2010 | SP2010 On-Prem to O365 | 10-15 GB | Metavis | 4-5 Days | 23 Members are working | Slowness and connection break. Contribution to it…network bandwidth, tool sometimes shows wrong results so manual verification is required to check its validity. This happens only for huge libraries or if folder hierarchy levels in a library is very deep | One PowerShell script to delete explorer view of the libraries as it is not supported in O365 | Customization part yet not faced but its development strategy would depend which type of space (dedicated or multi-tenant ) is bought.
Manufacturer of civil and military avionics and other aerospace products | SP 2007 | SP 2013 On-Prem | 2TB | Metalogix for migration of Data & Cipherpoint / SQL Server TDE for Encryption | 8 months | 8 months post POC as is migration and after that CAM based code re-engineering for future Office 365 migration. | Encryption reduced the performance of calculated columns lists which vendor fixed however not all the columns gets encrypted for which we find SQL Server Enterprise TDE option seems good. | Some custom coding for list migration.
One of the largest banks of Australia | WSS 3.0 | SP 2010 On-Prem | 6TB+ | DocAve 6 | 1 year | 1 Project Manager, 1 Architect onsite, 15 dev/Admin offshore, 3 Testers | Migration of permission from classic,windows claims ADFS. DocAve sync issues - Vendor provided numerous hotfixes. | Custom DocAve Automation and optimization scripts, Migration paper, Known issues and workarounds, Customization discovery Scripts and Governance framework | Ensuring for having premium support from vendor during migration.
Contract research organization providing | Moss 2007 | SP2013 On-prem | 1 TB | DocAve 6.2. Teamsites (60%) with no-coding, Publishing sites (20%) fully customized, InfoPath Forms based application (20%) | 6 months | 1 Architect (4 months), 4 developers, 1 migration expert, 2 admin, 1 Business Engagement Manager | Tool dependency, Had to wait for three hotfixes, Tool learning curve during initial migration | PowerShell scripts for identifying/comparing site size, IIS Rewrite module for site redirection | Well planned Site collection segregation with Full + Delta migration
An integrated energy and chemical company based in South Africa | SP 2010 | SP2013 On-Prem | 1.5 – 2 TB | Did not use any migration tools rather Microsoft’s default migration approach (DB Attach) is being be used | 2+ months only for SP 2010, SP 2013 is yet to start. | Development efforts required for SP 2013 and would be need for SP 2013 as well. | Heavy customizations and complicated 3rd party integrations. There are 160 custom solutions, integration with OpenText. DNS configurations/network issues. | N/A | We are changing the architecture for SP 2013 altogether for better performance and results followed by the best practices. Customer is also looking forward for Office 365 deployment, so we need to think on those lines as well.
Contract Logistics and Freight Management solutions provider worldwide | SP 2007 | SP2013 On-Prem | 3 TB+ | Default MS methodology, Chris’O Brian tool for export & Import | 2 Years | 170 PM | Large content DB (~1.5 TB) of single site collection , workflows, UI distortion , Heavy customization, Huge volume of data along with Unstructured format, Governance, heavily customization using SPD | Documents, Scripts and few utilities
World leader in memory and semiconductor technology | Moss 2007 & Documentum | SP2013 On-Pem | 1 TB+ | Metalogix | 10 Months | 7 resources | BI Issue Navigation Issue Chinese Character Issue Excel services scheduled power pivot refresh | N/A
One of the largest pharmaceutical companies in the world | Moss 2007 | SP2010 On-Prem | 500 GB approx. | Microsoft Database detach and attach with customization using VS 2010. Here is the Mysites upgrade process Approach • Re compile/ re write customized code against 2010 object model and deploy to 2010 environment • Create a new My sites web application and a new My Sites Host site collection in the 2010 environment. • Migrate the content databases hosting the personal site collections in 2007 My Sites to 2010 environment, and attach to the new My Sites web application• Associate the personal site collections to the respective user profiles • Update all the My Sites Site collections with the 2010 Master page • Enable self service site collection provisioning from the new My Sites web application • Update DNS to point to the new My Sites web application hosted in 2010 environment Similar approach was used for content database upgrade process. Content type hub was used to deploy the content types across site collections News gator was used for Newsfeed and socialization. | 1 year | 1 Year | Missing feature ID errors while attaching content database: Before attaching the content database you should deploy the 2007 WSP in 2010 environment Mysites migration using database detach and attach (Branding mysites host master page using stapling) Cleaning up of user profile from mysites which are no longer exist in AD User Profile BDC to BCS BCS(Conversion of Web services to WCF for fetching data from Oracle and SSO Configuration. The credentials used to connect to WCF services are be stored in Secure Store Service DB. BCS connects to WCF services using the metadata model and authenticates through Secure Store Services. The WCF Services in turn connect to Oracle ESA and retrieve values from appropriate tables to populate user profile properties. An import connection will be created for BCS in User Profile Synchronization service, and user profile properties can be synchronized with ESA as needed. Profiles are daily updated from oracle database. User profile data migration The user profile data from SharePoint 2007 SSP database is migrated into 2 separate databases in SharePoint 2010 during a database attach upgrade process. The user profile fields and values go into Profile database and if any taxonomy existed in the 2007 SSP database it is upgraded and moved into the Term Store used by Managed Metadata Services. When upgrade is performed, the taxonomy data are upgraded but needs to be moved explicitly into Term Store by running a PowerShell cmd. Upgrading SSP into SP 2010. | N/A | Agile methodology was used here. More than 30 developers were working on this project and it was T&M project. This was one of the most complicated projects with more than 60-70 customizations. NewsGator was also integrated and upgraded. Mysite was to be upgraded. BCS was used to fetch mysites personal page details from Oracle database and it used to sync the data on daily basis for user profile like manager details, department etc. FAST search was integrated for enterprise search.
Group of chemicals manufacturing companies | SP 2007 | SP 2010 | 2.5 TB | No tool was used. Content DB attach upgrade was done | 3 Months | 1 SP admin & 1 SP developer | • Rather than building a new server from scratch and SharePoint installed, a copy of the existing server machine was made and reconfigured. Lots of issues came since many configuration in the new server was still pointing to old database and had to be corrected. • Mysite databases were not migrated and users personal documents etc. had to be copied manually to the new mysite. • SharePoint designer workflows in MOSS failed to start after migration to SP2010 and had to be republished. • Export to excel out of the box functionality failed to work for a large list.
An American multinational technology company headquartered in Redmond | SP 2010 | SP 2013 | 500 GB to 1 TB approx. | Used the database attach method, no migration tools | N/A | N/A | Have identified performance problems in the virtual environment where the underlying Hyper-V servers had to have the Power Regulator (BIOS setting) changed to Maximum in order to increase performance. Had several other blockers, ranging from pages that leveraged a CAML query to search (had to be converted to REST due to performance/item count returned) to poor Usage database performance due to additional information logged in 2013. | N/A
An American public research, development and mfg. company | SP 2007 | SP 2010 | 1 TB | Custom Powershell Scripts were created for DB attach and Upgrades | SP 2010 Insatalltion - 4 Days Conetnt DB Upgrades - Done in Waves over 3 Weekends | >540 hrs | The existing SP 2007 application had to be moved to an Intermediate Farm >300 COntent DBs had to be upgraded | Powershell Scripts used for the upgrade can be reused | The upgrade was a combination of Inplace and Content DB attach method. The application tier was upgraded Inplace The DBs were upgraded by DB attach method